## Gantt Rough Data (hidden)
Proposal Submission to STB | Project Initiation |  | Stakeholder and Partner Finalisation | Permit and Compliance Preparation | Logistics and Resource Procurement | Staffing and Training | Marketing and Promotion | Event Operations and Setup | Post-Event Closure and Evaluation
Event Grant and Approval of Proposal | Proposal Submission to STB |  | Singapore Airlines Sponsorship | SFA Temporary Fair Permit | Secure rental of lighting equipment | Hiring of Event Staff | Finalisation of Microsite design | Initial meter reading | Payment of utilities
Submission of NRTOL | Event Grant and Approval of Proposal |  | Nestle Sponsorship and Milo van schedule | SPF Class 5A Liquor Licence | Secure rental of tentage | Hiring of Janitors | Microsite Launch | Schedule transportation | Disbursement of salaries for supporting staff
Hiring of Event Staff | Submission of NRTOL |  | Tiger Beer Sponsorship | SCDF P&FM Storage Licence (Liquid) | Secure rental of audio equipment | Hiring of Security | Announcement of event dates | Staff briefing | Disbursement of revenue to hawkers
Hiring of Janitors | Approval of NRTOL |  | GrabFood Sponsorship | SCDF Temporary Change of Use | Secure rental of food stalls | Hiring of Medic |  | Pre-con survey | Return of security deposit from URA
Hiring of Security | Security Deposit Payment to URA |  | Liason with hawkers for festival | BCA Advertising Licence | Secure rental of fence barrier | Hiring of Appointed Licence Electrical Worker |  | Liase with URA managing agent for site takeover | Payment of subcontractors
Hiring of Medic | Submission of Single Line Diagram |  | <Need one more sponsor> | Public Entertainment Licence | Purchase of Gas |  |  |  | Evaluation of budget and overall revenue
Hiring of Appointed Licence Electrical Worker |  |  | Confirming list of participating hawkers | Income Event Liability Plan | Printing of Culinary Passports |  |  |  | Return of all rented equipment
Purchase of Gas |  |  |  | PUB usage of water point | Secure rental of 6-seater bench |  |  |  | Return of equipment to warehouse
Printing of Culinary Passports |  |  |  | PUB clearance for sewerage | Purchase of blank passports with NFC chip
Secure rental of 6-seater bench |  |  |  |  | Secure rental of container toilets
Purchase of blank passports with NFC chip |  |  |  |  | Printing of Crew T-shirts
Secure rental of lighting equipment |  |  |  |  | Purchase of biodegradable cutlery
Secure rental of tentage |  |  |  |  | Printing of signages
Secure rental of audio equipment |  |  |  |  | Purchase of walkie-talkies
Secure rental of food stalls |  |  |  |  | Printing of food menus
Secure rental of fence barrier
Liason with hawkers for festival | Month | Week | Entry | Remark
SFA Temporary Fair Permit | April | Week 1 | Proposal Submission to STB | Submission of Event Proposal, factoring in time for evaluation and critique from STB
SPF Class 5A Liquor Licence |  | Week 3 | Approval of Proposal
SCDF P&FM Storage Licence (Liquid) |  | Week 3 | Submission of Grant Application to STB | Submission of request for Grant Application to STB (70%)
SCDF Temporary Change of Use |  | Week 5 | Approval of Grant Application
BCA Advertising Licence | May |  | Liasing with Hawkers for festival | Meeting with top hawkers around SG to invite them to participate in our festival
Public Entertainment Licence |  |  | Meeting with potential sponsors for event | Potential Sponsors in Mind: Singapore Airlines, Nestle, Tiger Beer and GrabFood
Income Event Liability Plan | June |  | Confirming list of participating hawkers | Finalization of Participating Hawkers in our festival
Singapore Airlines Sponsorship |  |  | Secure Sponsors | Confirmation of all particpating sponsors in our event
Nestle Sponsorship and Milo van schedule | July | Week 1 | Submission of Licence Applications | SFA Temporary Fair, SPF Class 5A Liquor, SCDF P&FM Storage License, SCDF Temporary Change of Use, BCA Advertising, Public Entertainment
Tiger Beer Sponsorship |  |  | Application of Insurance | Income Event Liability Plan
GrabFood Sponsorship |  | Week 2 | Licence Approval
PUB usage of water point |  |  | Insurance Coverage Approval
Project Inquiry and Rate Request for Microsite Developer
Project Inquiry and Rate Request for Zermatt Neo
PUB clearance for sewerage |  | Week 3 | Submission of URA event application form
Submission of Single Line Diagram |  |  | Issuance of in-principle approval
Marketing & Communications Strategy Submission to STB
Joint inspection and initial meter reading |  | Week 4 | Submission of relevant documents to URA | Submission of supporting documents
| August | Week 1 | Marketing & Communications Strategy Approval from STB
Filming for "Voice of Hawker Culture" & "Hawker Legends & New Voices" Collaterals
Security Deposit Payment to URA |  | Week 2 | Issuance of NRTOL | Approval received on our proposal from BES/URA
Begin work on Visit SG introductory Press Release
Begin work on Sep's Social Media Collaterals
Payment of utilities |  | Week 3 | Rental Inquiries | Sourcing out Logistics
Visit SG Introductory Press Release Submission to STB
Social Media Collaterals (Sep) Submission to STB
Confirming list of participating hawkers |  | Week 4 | Submission of printouts | Sending our events artworks for printing
Visit SG Introductory Press Release Approval from STB
Social Media Collaterals (Sep) Approval from STB
|  |  | Finalise Engagement Contract & Commencement of Project with Mediacorp | For Radio Advertisement
Finalise Engagement Contract & Commencement of Project with TSL
Finalise Engagement Contract & Commencement of Project with Microsite Developer
Finalise Engagement Contract & Commencement of Project with Zermatt Neo
Begin work on details for TSL Press Release
Begin work on Microsite collaterals and content
| September | Week 1 | Announcement of Event Dates & Location
TSL Press Release details Submission to STB
Disbursement of salaries for supporting staff |  |  | Microsite collaterals and content Submission to STB
Disbursement of revenue to hawkers |  | Week 2 | List Hiring Ads for Support Staff | Event Staff, Janitors, Medic, Appointed Licence Electrical Worker
TSL Press Release details Approval from STB
Microsite collaterals and content Approval from STB
Return of security deposit from URA |  |  | Begin work on Oct's Social Media Collaterals
Payment of subcontractors |  | Week 3 | Secure and Schedule Rentals
Finalisation of Microsite design |  |  | Secure Printings | Signages, T-Shirts, Culinary Passports, Fence Banners
Send finalised details to TSL
Send finalised collaterals and content to Microsite Developer
Social Media Collaterals (Oct) Submission to STB
Printing of Crew T-shirts |  | Week 4
Secure rental of container toilets |  |  | Secure Staff
Social Media Collaterals (Oct) Approval from STB
Schedule transportation | October | Week 1 | Purchase of logistics
|  | Week 2 | Begin work on Social Media Nov's Collaterals
Microsite Launch |  | Week 3 | Schedule Transportation
Finalised Microsite Submission to STB
Finalised TSL Press Release Submission to STB
|  |  | Social Media Collaterals (Nov) Submission to STB | Collaterals will also include Final Microsite & TSL Press Release
|  | Week 4 | Finalised Microsite Approval from STB
Finalised TSL Press Release Approval from STB
|  |  | Social Media Collaterals (Nov) Approval from STB | Collaterals will also include Final Microsite & TSL Press Release
Purchase of biodegradable cutlery | November | Week 2 | Marketing Team to work on Dec's (Pre-Event) Collaterals
Marketing Team to work on Dec's (Pre-Event) Collaterals
Printing of signages |  |  | Hawker Pre-event Conduct Training
|  | Week 3 | Marketing & Communications Collaterals (Dec) Submission to STB
Purchase of walkie-talkies |  |  | Final check through on every variable
|  | Week 4 | Marketing & Communications Collaterals (Dec) Submission to STB
Printing of food menus | Event Dates |  | Pre-con survey
Evaluation of budget and overall revenue |  |  | Initial meter reading
Return of all rented equipment |  |  | Liase with URA managing agent for site takeover
Return of equipment to warehouse |  |  | Return of equipment to warehouse
Week 1
| December | Week 3 | Reinstatement of State Land
Payment of utilities
Return of security deposit from URA
Return of all rented equipment
|  | Week 4 | Payment of subcontractors
Disbursement of revenue to hawkers
Disbursement of salaries for supporting staff
| January | Week 1 | Evaluation of budget and overall revenue | For in-house evaluation of success
Evaluation of quantitative and qualitative objectives
Submission of post-event evaluation to STB

## Gantt Chart
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Hawker Legacy: Flavours of SG Planning Timeline
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. | Planning Timeline Duration: | 9 Months
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 | [6 empty] | Week 26 | [6 empty] | Week 27 | [6 empty] | Week 28 | [6 empty] | Week 29 | [6 empty] | Week 30 | [6 empty] | Week 31 | [6 empty] | Week 32 | [6 empty] | Week 33 | [6 empty] | Week 34 | [6 empty] | Week 35 | [6 empty] | Week 36 | [6 empty] | Week 37 | [6 empty] | Week 38 | [6 empty] | Week 39 | [6 empty] | Week 40 | [6 empty] | Week 41 | [6 empty] | Week 42 | [6 empty] | Week 43 | [6 empty] | Week 44
|  |  |  | MONTH OF APRIL | [29 empty] | MONTH OF MAY | [30 empty] | MONTH OF JUNE | [29 empty] | MONTH OF JULY | [30 empty] | MONTH OF AUGUST | [30 empty] | MONTH OF SEPTEMBER | [29 empty] | MONTH OF OCTOBER | [30 empty] | MONTH OF NOVEMBER | [29 empty] | MONTH OF DECEMBER | [30 empty] | MONTH OF JANUARY
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASKS (according to levels) | START DATE | END DATE | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Project Initiation
| Submission of Proposal to STB | 2024-04-01 | 2024-04-18 | bar: MONTH OF APRIL 1
| Proposal Approval from STB | 2024-04-02 | 2024-04-18 | bar: MONTH OF APRIL 2 to MONTH OF APRIL 18
| Submission of Grant Application to STB | 2024-04-19 | 2024-04-19 | bar: MONTH OF APRIL 19
| Approval of Grant Application from STB | 2024-04-20 | 2024-04-27 | bar: MONTH OF APRIL 20
| Submission of URA Event Rental Application Form | 2024-07-15 | 2024-07-15 | bar: MONTH OF JULY 15
| URA's Issuance of In-Principle Approval | 2024-07-16 | 2024-07-21 | bar: MONTH OF JULY 16 to MONTH OF JULY 21
| Submission of NRTOL Documents to URA | 2024-07-22 | 2024-07-22 | bar: MONTH OF JULY 22
| URA's Issuance of NRTOL | 2024-07-23 | 2024-08-04 | bar: MONTH OF JULY 23 to MONTH OF AUGUST 4
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Stakeholder and Partnerships
| Project Pitch for Sponsorship to Singapore Airlines | 2024-05-06 | 2024-05-17 | bar: MONTH OF MAY 6 to MONTH OF MAY 17
| 1st Round of Invitations to Hawkers | 2024-05-06 | 2024-05-19 | bar: MONTH OF MAY 6 to MONTH OF MAY 19
| Project Pitch to Solace Studios | 2024-05-06 | 2024-05-19 | bar: MONTH OF MAY 6 to MONTH OF MAY 19
| Project Pitch to Ya Kun Kaya Toast | 2024-05-06 | 2024-05-19 | bar: MONTH OF MAY 6 to MONTH OF MAY 19
| Project Pitch for Sponsorship to Nestle | 2024-05-13 | 2024-05-24 | bar: MONTH OF MAY 13 to MONTH OF MAY 24
| Project Pitch for Sponsorship to Tiger Beer | 2024-05-20 | 2024-05-31 | bar: MONTH OF MAY 20 to MONTH OF MAY 31
| Consolidation of 1st Round Reponses from Hawkers | 2024-05-20 | 2024-06-02 | bar: MONTH OF MAY 20 to MONTH OF JUNE 2
| Finalise Sponsorship Contract with Singapore Airlines | 2024-05-27 | 2024-06-02 | bar: MONTH OF MAY 27 to MONTH OF JUNE 2
| 2nd Round of Invitations to Hawkers | 2024-06-03 | 2024-06-09 | bar: MONTH OF JUNE 3 to MONTH OF JUNE 9
| Finalise Sponsorship Contract with Nestle | 2024-06-03 | 2024-06-09 | bar: MONTH OF JUNE 3 to MONTH OF JUNE 9
| Project Pitch for Sponsorship to Grab | 2024-06-03 | 2024-06-11 | bar: MONTH OF JUNE 3 to MONTH OF JUNE 11
| Finalise Sponsorship Contract with Tiger Beer | 2024-06-10 | 2024-06-16 | bar: MONTH OF JUNE 10 to MONTH OF JUNE 16
| Consolidation of 2nd Round Responses from Hawkers | 2024-06-10 | 2024-06-23 | bar: MONTH OF JUNE 10 to MONTH OF JUNE 23
| Finalise Engagement Contract with Ya Kun Kaya Toast | 2024-06-17 | 2024-06-23 | bar: MONTH OF JUNE 17 to MONTH OF JUNE 23
| Finalise Engagement Contract with Solace Studios | 2024-06-17 | 2024-06-23 | bar: MONTH OF JUNE 17 to MONTH OF JUNE 23
| Finalise Sponsorship Contract with Grab | 2024-06-17 | 2024-06-23 | bar: MONTH OF JUNE 17 to MONTH OF JUNE 23
| Confirm List of Participating Hawkers | 2024-06-24 | 2024-06-30 | bar: MONTH OF JUNE 24 to MONTH OF JUNE 30
| Confirm List of Sponsors | 2024-06-24 | 2024-06-30 | bar: MONTH OF JUNE 24 to MONTH OF JUNE 30
Sample phase title block | Permits, Compliance & Insurance
| Submission of Income Event Liability Plan (Insurance) Application | 2024-05-12 | 2024-05-12 | bar: MONTH OF MAY 12
| SFA Temporary Fair Permit Submission | 2024-05-13 | 2024-05-13 | bar: MONTH OF MAY 13
| SCDF P&FM Storage Licence (Liquid) Submission | 2024-05-13 | 2024-05-13 | bar: MONTH OF MAY 13
| SFA Temporary Fair Permit Approval | 2024-05-14 | 2024-05-26 | bar: MONTH OF MAY 14 to MONTH OF MAY 26
| SCDF P&FM Storage Licence (Liquid) Approval | 2024-05-14 | 2024-05-26 | bar: MONTH OF MAY 14 to MONTH OF MAY 26
| SPF Class 5A Liquor Licence Submission | 2024-05-27 | 2024-05-27 | bar: MONTH OF MAY 27
| SCDF Temporary Change of Use Submission | 2024-05-27 | 2024-05-27 | bar: MONTH OF MAY 27
| Public Entertainment Licence Submission | 2024-05-27 | 2024-05-27 | bar: MONTH OF MAY 27
| BCA Advertising Licence Submission | 2024-05-27 | 2024-05-27 | bar: MONTH OF MAY 27
| SPF Class 5A Liquor Licence Approval | 2024-05-28 | 2024-06-09 | bar: MONTH OF MAY 28 to MONTH OF JUNE 9
| SCDF Temporary Change of Use Approval | 2024-05-28 | 2024-06-09 | bar: MONTH OF MAY 28 to MONTH OF JUNE 9
| Public Entertainment Licence Approval | 2024-05-28 | 2024-06-09 | bar: MONTH OF MAY 28 to MONTH OF JUNE 9
| BCA Advertising Licence Approval | 2024-05-28 | 2024-06-09 | bar: MONTH OF MAY 28 to MONTH OF JUNE 9
| Final Consolidation of Permits and Licences | 2024-06-10 | 2024-06-16 | bar: MONTH OF JUNE 10
| Income Event Liability Plan (Insurance) Approval | 2024-06-13 | 2024-06-26 | bar: MONTH OF JUNE 13; MONTH OF JUNE 20
| Request Risk Assessment from Vendors (Yakun, Solace, Tiger Beer, Nestle, MediaPlus, NETS, TechnologyRental, SingGas, Natoma, Suits) | 2024-09-16 | 2024-09-16 | bar: MONTH OF SEPTEMBER 16
| Receive Risk Assessment from Vendors (Yakun, Solace, Tiger Beer, Nestle, MediaPlus, NETS, TechnologyRental, SingGas, Natoma, Suits) | 2024-09-29 | 2024-09-29 | bar: MONTH OF SEPTEMBER 29
Sample phase title block | Logistics and Resource Procurement
| Purchase of NFC Chips | 2024-08-19 | 2024-08-19 | bar: MONTH OF AUGUST 19
| Schedule Rental for Tentage | 2024-08-19 | 2024-08-19 | bar: MONTH OF AUGUST 19
| Schedule Rental Prices for Food Stalls | 2024-08-19 | 2024-08-19 | bar: MONTH OF AUGUST 19
| Schedule Rental for Sandwich Board | 2024-08-19 | 2024-08-19 | bar: MONTH OF AUGUST 19
| Schedule Rental for 6-Seater Benches | 2024-08-19 | 2024-08-19 | bar: MONTH OF AUGUST 19
| Schedule Rental for Truss Framework | 2024-08-19 | 2024-08-19 | bar: MONTH OF AUGUST 19
| Submmision of Culinary Passport design to printing agency for production | 2024-08-26 | 2024-08-26 | bar: MONTH OF AUGUST 26
| Submmision of Menu design (for sandwich board) to printing agency for production | 2024-08-26 | 2024-08-26 | bar: MONTH OF AUGUST 26
| Submission of Evacuation Route Map to printing agency for production | 2024-08-26 | 2024-08-26 | bar: MONTH OF AUGUST 26
Sub | Submmision of Entrance & Exit design to printing agency for production | 2024-08-26 | 2024-08-26 | bar: MONTH OF AUGUST 26
| Submission of Passport Counter Banner to printing agency for production | 2024-08-26 | 2024-08-26 | bar: MONTH OF AUGUST 26
| Submission of Storefront design to printing agency for production | 2024-08-26 | 2024-08-26 | bar: MONTH OF AUGUST 26
Submission of Fence Barrier design to printing agency for production | bar: MONTH OF SEPTEMBER 16
| Schedule Rental for Fence Barriers | 2024-09-16 | 2024-09-16 | bar: MONTH OF SEPTEMBER 16
| Schedule Rental for Lighting Equipment | 2024-09-16 | 2024-09-16 | bar: MONTH OF SEPTEMBER 16
| Schedule Rental for CERT Equipment (Safety Goggles, Safety Gloves, Blankets, First Aid Kit, AED, and Foldable Stretcher) | 2024-09-23 | 2024-09-23 | bar: MONTH OF SEPTEMBER 16
| Schedule Rental for Portable Toilets | 2024-09-23 | 2024-09-23 | bar: MONTH OF SEPTEMBER 23
| Submission of Crew T-Shirts Design for production | 2024-10-07 | 2024-10-07 | bar: MONTH OF OCTOBER 7
| Schedule Rental for Audio Equipment | 2024-10-07 | 2024-10-07 | bar: MONTH OF OCTOBER 7
| Schedule Rental for NETS Reader | 2024-10-07 | 2024-10-07 | bar: MONTH OF OCTOBER 7
| Schedule Rental for NFC Reader | 2024-10-07 | 2024-10-07 | bar: MONTH OF OCTOBER 7
| Schedule Rental for Fire Extinguishers | 2024-10-07 | 2024-10-07 | bar: MONTH OF OCTOBER 7
| Purchase of Customised Stamps | 2024-10-07 | 2024-10-07 | bar: MONTH OF OCTOBER 7
| Purchase of LPG Cylinders | 2024-10-07 | 2024-10-07 | bar: MONTH OF OCTOBER 7
| Purchase of Gas Regulators | 2024-10-07 | 2024-10-07 | bar: MONTH OF OCTOBER 7
| Purchase of Customised Cutlery | 2024-10-07 | 2024-10-07 | bar: MONTH OF OCTOBER 7
| Purchase of Loudhailer | 2024-10-07 | 2024-10-07 | bar: MONTH OF OCTOBER 7
| Purchase of CERT Equipment (Safety Helmets and Boots) | 2024-10-07 | 2024-10-07 | bar: MONTH OF OCTOBER 7
| Schedule Rental for Walkie-Talkies | 2024-10-21 | 2024-10-21 | bar: MONTH OF OCTOBER 7
| Schedule of Lorry Rental for Transportation | 2024-10-21 | 2024-10-21 | bar: MONTH OF OCTOBER 21
| Receive all Printed & Purchased Items (except gas) | 2024-11-04 | 2024-11-04 | bar: MONTH OF NOVEMBER 4
This is an empty row | Festival Personnel
| Finalise contract with Natoma Pte Ltd (Cleaning Company) - Includes Waste Bins, Cleaning Staff, General Waste Collectors (GWC) | 2024-09-09 | 2024-09-15 | bar: MONTH OF SEPTEMBER 9 to MONTH OF SEPTEMBER 15
| Finalise Contract with Suits Security Solutions Detail | 2024-09-09 | 2024-09-15 | bar: MONTH OF SEPTEMBER 9 to MONTH OF SEPTEMBER 15
| List Hiring Ads for Festival Staff | 2024-09-09 | 2024-09-22 | bar: MONTH OF SEPTEMBER 9 to MONTH OF SEPTEMBER 22
| Implement Incident Management Process Course | 2024-09-16 | 2024-09-16 | bar: MONTH OF SEPTEMBER 16
| WSQ Respond to Fire Incident in Workplace Course | 2024-09-17 | 2024-09-18 | bar: MONTH OF SEPTEMBER 17 to MONTH OF SEPTEMBER 18
| CERT First Aid Course | 2024-09-19 | 2024-09-19 | bar: MONTH OF SEPTEMBER 19
| Consolidate all Festival Personnel List | 2024-09-23 | 2024-10-29 | bar: MONTH OF SEPTEMBER 23 to MONTH OF SEPTEMBER 29
| Send Guidelines and FAQ sheet to Hawkers | 2024-12-02 | 2024-12-02 | bar: MONTH OF DECEMBER 2
| Online Festival Briefing for all Stakeholders | 2024-12-12 | 2024-12-12 | bar: MONTH OF DECEMBER 12
Marketing and Communication (Color-Coded based on content pillars)
| Marketing & Communications Strategy Submission to STB | 2024-07-19 | 2024-07-19 | bar: MONTH OF JULY 19
| Marketing & Communications Strategy Refinement & Approval from STB | 2024-07-20 | 2024-07-28 | bar: MONTH OF JULY 20 to MONTH OF JULY 28
| Filming for "Voice of Hawker Culture" & "Hawker Legends & New Voices" | 2024-07-29 | 2024-08-04 | bar: MONTH OF JULY 29 to MONTH OF AUGUST 4
| Designing of Shirts, Menu, Culinary Passport, and Banners | 2024-07-29 | 2024-08-11 | bar: MONTH OF JULY 29 to MONTH OF AUGUST 11
| Begin work on Visit SG introductory Press Release | 2024-08-05 | 2024-08-11 | bar: MONTH OF AUGUST 5 to MONTH OF AUGUST 11
| Begin work on Sep's Social Media Collaterals | 2024-08-05 | 2024-08-11 | bar: MONTH OF AUGUST 5 to MONTH OF AUGUST 11
| Submission of Shirts, Menu, Culinary Passport, and Banner Design to STB | 2024-08-12 | 2024-08-12 | bar: MONTH OF AUGUST 12
| Shirts, Menu, Culinary Passport, and Banner Design refinement & approval from STB | 2024-08-13 | 2024-08-25 | bar: MONTH OF AUGUST 13 to MONTH OF AUGUST 25
| VisitSG Introductory Press Release Submission to STB | 2024-08-14 | 2024-08-14 | bar: MONTH OF AUGUST 14
| Social Media Collaterals (Sep) Submission to STB | 2024-08-14 | 2024-08-14 | bar: MONTH OF AUGUST 14
| VisitSG Introductory Press Release Refinements & Approval from STB | 2024-08-15 | 2024-08-25 | bar: MONTH OF AUGUST 15; MONTH OF AUGUST 19 to MONTH OF AUGUST 25
| Social Media Collaterals (Sep) Refinements & Approval from STB | 2024-08-15 | 2024-08-25 | bar: MONTH OF AUGUST 15; MONTH OF AUGUST 19 to MONTH OF AUGUST 25
| Finalise Engagement Contract with Mediacorp | 2024-08-19 | 2024-08-25 | bar: MONTH OF AUGUST 19 to MONTH OF AUGUST 25
| Finalise Engagement Contract with TSL | 2024-08-19 | 2024-08-25 | bar: MONTH OF AUGUST 19 to MONTH OF AUGUST 25
| Finalise Engagement Contract with Web Development Agency (MediaPlus) | 2024-08-19 | 2024-08-25 | bar: MONTH OF AUGUST 19 to MONTH OF AUGUST 25
| Finalise Engagement Contract with Zermatt Neo | 2024-08-19 | 2024-08-25 | bar: MONTH OF AUGUST 19 to MONTH OF AUGUST 25
| Begin work on details for TSL Press Release | 2024-08-19 | 2024-09-01 | bar: MONTH OF AUGUST 19 to MONTH OF SEPTEMBER 1
| Begin work on Microsite collaterals and content | 2024-08-19 | 2024-09-01 | bar: MONTH OF AUGUST 19 to MONTH OF SEPTEMBER 1
| Launch of VisitSG Introductory Festival Press Release | 2024-09-01 | 2024-09-01 | bar: MONTH OF SEPTEMBER 1
| Posting of Festival Announcement (Paid Ads) | 2024-09-01 | 2024-09-14 | bar: MONTH OF SEPTEMBER 1 to MONTH OF SEPTEMBER 14
| TSL Press Release details Submission to STB | 2024-09-02 | 2024-09-08 | bar: MONTH OF SEPTEMBER 2
| Microsite collaterals and content Submission to STB | 2024-09-02 | 2024-09-08 | bar: MONTH OF SEPTEMBER 2
| TSL Press Release details Refinements & Approval from STB | 2024-09-03 | 2024-09-15 | bar: MONTH OF SEPTEMBER 3 to MONTH OF SEPTEMBER 15
| Microsite collaterals and content Refinements & Approval from STB | 2024-09-03 | 2024-09-15 | bar: MONTH OF SEPTEMBER 3 to MONTH OF SEPTEMBER 15
| Posting of “Save the Date” Story | 2024-09-08 | 2024-12-08 | bar: MONTH OF SEPTEMBER 8; MONTH OF SEPTEMBER 15; MONTH OF SEPTEMBER 22; MONTH OF SEPTEMBER 29; MONTH OF OCTOBER 6; MONTH OF OCTOBER 13; MONTH OF OCTOBER 20; MONTH OF OCTOBER 27; MONTH OF NOVEMBER 3; MONTH OF NOVEMBER 10; MONTH OF NOVEMBER 17; MONTH OF NOVEMBER 24; MONTH OF DECEMBER 1; MONTH OF DECEMBER 8
| Begin work on Oct's Social Media Collaterals | 2024-09-09 | 2024-09-15 | bar: MONTH OF SEPTEMBER 9 to MONTH OF SEPTEMBER 15
| Posting of "Voices of Hawker Culture" | 2024-09-11 | 2024-09-13 | bar: MONTH OF SEPTEMBER 11; MONTH OF SEPTEMBER 13
| Submission of finalised details to TSL | 2024-09-16 | 2024-09-16 | bar: MONTH OF SEPTEMBER 16
| Submission of finalised collaterals and content to Web Development Agency (MediaPlus) | 2024-09-16 | 2024-09-16 | bar: MONTH OF SEPTEMBER 16
| Social Media Collaterals (Oct) Submission to STB | 2024-09-16 | 2024-09-16 | bar: MONTH OF SEPTEMBER 16
| Social Media Collaterals (Oct) Refinements & Approval from STB | 2024-09-17 | 2024-09-29 | bar: MONTH OF SEPTEMBER 17 to MONTH OF SEPTEMBER 29
| Posting of "Fun Facts & Hawker History" | 2024-09-18 | 2024-09-20 | bar: MONTH OF SEPTEMBER 18; MONTH OF SEPTEMBER 20
| Posting of "Hawker Legends & New Voices" | 2024-09-23 | 2024-09-28 | bar: MONTH OF SEPTEMBER 23; MONTH OF SEPTEMBER 25; MONTH OF SEPTEMBER 27
| Begin work on VisitSG Full Press Release | 2024-09-30 | 2024-10-13 | bar: MONTH OF SEPTEMBER 30 to MONTH OF OCTOBER 13
| Begin work on Nov's Social Media Collaterals | 2024-09-30 | 2024-10-13 | bar: MONTH OF SEPTEMBER 30 to MONTH OF OCTOBER 13
| Launch of Social Media Contest Post | 2024-10-01 | 2024-10-01 | bar: MONTH OF OCTOBER 1
| Posting of Daily Hawker Feature Posts | 2024-10-02 | 2024-10-27 | bar: MONTH OF OCTOBER 2 to MONTH OF OCTOBER 6; MONTH OF OCTOBER 9 to MONTH OF OCTOBER 13; MONTH OF OCTOBER 16 to MONTH OF OCTOBER 20; MONTH OF OCTOBER 23 to MONTH OF OCTOBER 27
| VisitSG Full Press Release Submission to STB | 2024-10-14 | 2024-10-14 | bar: MONTH OF OCTOBER 14
| Social Media Collaterals (Nov) Submission to STB | 2024-10-14 | 2024-10-14 | bar: MONTH OF OCTOBER 14
| Finalised Microsite Submission to STB | 2024-10-14 | 2024-10-14 | bar: MONTH OF OCTOBER 14
| Finalised TSL Press Release Submission to STB | 2024-10-14 | 2024-10-14 | bar: MONTH OF OCTOBER 14
| VisitSG Full Press Release Refinements & Approval from STB | 2024-10-15 | 2024-10-27 | bar: MONTH OF OCTOBER 15 to MONTH OF OCTOBER 27
| Social Media Collaterals (Nov) Refinements & Approval from STB | 2024-10-15 | 2024-10-27 | bar: MONTH OF OCTOBER 15 to MONTH OF OCTOBER 27
| Finalised Microsite Refinements & Approval from STB | 2024-10-15 | 2024-10-27 | bar: MONTH OF OCTOBER 15 to MONTH OF OCTOBER 27
| Finalised TSL Press Release Refinements & Approval from STB | 2024-10-15 | 2024-10-27 | bar: MONTH OF OCTOBER 15 to MONTH OF OCTOBER 27
| End of Social Media Contest | 2024-10-31 | 2024-10-31 | bar: MONTH OF OCTOBER 31
| Launch of Festival Microsite | 2024-11-01 | 2024-11-01 | bar: MONTH OF NOVEMBER 1
| Posting of Culinary Passport Reveal | 2024-11-01 | 2024-11-01 | bar: MONTH OF NOVEMBER 1
| Posting of Solace Studios Photo Booth Reveal | 2024-11-02 | 2024-11-02 | bar: MONTH OF NOVEMBER 2
| Send list of winners to STB for approval | 2024-11-02 | 2024-11-02 | bar: MONTH OF NOVEMBER 2
| Contact Winners to give out prizes | 2024-11-03 | 2024-11-03 | bar: MONTH OF NOVEMBER 3
| Begin work on Mediacorp Radio Ads script | 2024-11-04 | 2024-11-12 | bar: MONTH OF NOVEMBER 4 to MONTH OF NOVEMBER 12
| Begin work on Dec's Social Media Collaterals | 2024-11-04 | 2024-11-12 | bar: MONTH OF NOVEMBER 4 to MONTH OF NOVEMBER 12
| Posting of Hawker Masterclass Reveal | 2024-11-05 | 2024-11-05 | bar: MONTH OF NOVEMBER 5
| Posting of @zermattneo Activation Reveal | 2024-11-08 | 2024-11-08 | bar: MONTH OF NOVEMBER 8
| Launch of VisitSG Full Press Release | 2024-11-11 | 2024-11-11 | bar: MONTH OF NOVEMBER 11
| Launch of TSL Press Release | 2024-11-13 | 2024-11-13 | bar: MONTH OF NOVEMBER 13
| Radio Ads script Submission to STB | 2024-11-13 | 2024-11-13 | bar: MONTH OF NOVEMBER 13
| Social Media Collaterals (Dec) Submission to STB | 2024-11-13 | 2024-11-13 | bar: MONTH OF NOVEMBER 13
| Social Media Collaterals (Dec) Refinements & Approval from STB | 2024-11-14 | 2024-11-24 | bar: MONTH OF NOVEMBER 14 to MONTH OF NOVEMBER 24
| Radio Ads script Refinements & Approval from STB | 2024-11-14 | 2024-11-24 | bar: MONTH OF NOVEMBER 14 to MONTH OF NOVEMBER 24
| Submission of Radio Ads Script to Mediacorp | 2024-11-25 | 2024-11-25 | bar: MONTH OF NOVEMBER 25
| Posting of Festival Reminder (Paid Ads) | 2024-12-01 | 2024-12-12 | bar: MONTH OF DECEMBER 1 to MONTH OF DECEMBER 9
| Broadcast of Mediacorp Radio Ads | 2024-12-10 | 2024-12-12 | bar: MONTH OF DECEMBER 10
| Zermatt's Livestream & IGS Posting | 2024-12-13 | 2024-12-13 | bar: MONTH OF DECEMBER 13
| Marketing Team to conduct street interviews at festival | 2024-12-13 | 2024-12-15 | bar: MONTH OF DECEMBER 13
| Posting of festival-day street interviews | 2024-12-13 | 2024-12-15 | bar: MONTH OF DECEMBER 13
| Marketing Team to capture real-time festival updates | 2024-12-13 | 2024-12-15 | bar: MONTH OF DECEMBER 13
| Posting of real-time festival updates | 2024-12-13 | 2024-12-15 | bar: MONTH OF DECEMBER 13
| Reposting of UGC | 2024-12-13 | 2024-12-15 | bar: MONTH OF DECEMBER 13
| Posting of Street interviews | 2024-12-13 | 2024-12-15 | bar: MONTH OF DECEMBER 13
| Posting of Post-Festival Street interviews | 2024-12-16 | 2024-12-16 | bar: MONTH OF DECEMBER 16
| Posting of compiled UGC Round-Up | 2024-12-16 | 2024-12-16 | bar: MONTH OF DECEMBER 16
| Posting of Appreciation to Attendees | 2024-12-16 | 2024-12-16 | bar: MONTH OF DECEMBER 16
| Begin work on VisitSG Post-Event Press Release | 2024-12-16 | 2024-12-22 | bar: MONTH OF DECEMBER 16 to MONTH OF DECEMBER 22
| VisitSG Post-Event Press Release Submission to STB | 2024-12-23 | 2024-12-23 | bar: MONTH OF DECEMBER 23
| VisitSG Post-Event Press Release Refinements & Approval from STB | 2024-12-24 | 2024-12-29 | bar: MONTH OF DECEMBER 24 to MONTH OF DECEMBER 29
| Launch of VisitSG Post-Event Press Release | 2024-12-30 | 2024-12-30 | bar: MONTH OF DECEMBER 30
Event Set-up
| Receiving of Rented Equipment and Infrastructure | 2024-12-12 | 2024-12-12 | bar: MONTH OF DECEMBER 12
| Pre-Con Survey & Initial Meter Reading with URA Managing Agent for Site Takeover | 2024-12-12 | 2024-12-12 | bar: MONTH OF DECEMBER 12
| Festival Set-up | 2024-12-12 | 2024-12-12 | bar: MONTH OF DECEMBER 12
Post-Event Closure
| URA Inspection and Handover of State Land | 2024-12-16 | 2024-12-16 | bar: MONTH OF DECEMBER 16
| Return of All Rented Equipment | 2024-12-16 | 2024-12-16 | bar: MONTH OF DECEMBER 16
| Evaluation of Budget and Revenue Generated | 2024-12-16 | 2024-12-22 | bar: MONTH OF DECEMBER 16 to MONTH OF DECEMBER 22
| Return of Security Deposit from URA | 2024-12-23 | 2024-12-29 | bar: MONTH OF DECEMBER 23 to MONTH OF DECEMBER 29
| Disbursement of Revenue to Hawkers | 2024-12-30 | 2025-01-05 | bar: MONTH OF DECEMBER 30 to MONTH OF JANUARY 5
| Disbursement of Salaries to Supporting Staff | 2024-12-30 | 2025-01-05 | bar: MONTH OF DECEMBER 30 to MONTH OF JANUARY 5
| Closure of Event's Financial Accounts | 2025-01-06 | 2025-01-12 | bar: MONTH OF JANUARY 6 to MONTH OF JANUARY 12
| Submission of Post-Event Report to STB | 2025-01-13 | 2025-01-13 | bar: MONTH OF JANUARY 13

## Budget Rough Data (hidden)
Details | Price ($) | Details | Remarks
Event Rental Space
S1 | 6943.5
S2 | 11125.5
S1 + S2 (Set-up) | 602.4 |  | For day 0
S1 + S2 (Teardown) | 602.4 |  | For day 3
Total | 19273.8
Manpower
Event Staff | 2340 | 8 passport staff, 5 ushers, $12/hr
Cleaner | 1200 | 5 cleaners, $16/hr
Security | 2790 | 12 personnel, $15.50/hr
Medic | 3300 | 2 teams consisting of 1 drivers, 1 paramedics
Appointed Licensed Electrical Worker (LEW) | 3000 |  | Inclusive of Single Line Diagram of event
Total | 12630
Logistics
Seating Area | 12600 | 6-seater benches, $50/day, 84pcs
Water Supply | 440 | $1.66/m3
Cooling System | 1135 | $1.66/m3
Electric Supply | 1920 | $0.29/kWh
NFC Chip | 4000 | $0.50/chip, 8000pcs
Lighting Equipment | 2500
Gas | 975 | $39/tank, 14kg LPG, 25pcs
Tentage | 12000 | $600/gazebo, 20pcs
Audio Equipment | 1500 |  | Inclusive of 4x speakers, 4x speaker stands, 1x 10 channel mixer, 2x wireless microphone | Hiring of Scrap Disposal after the event
Food Stalls | 20000 | $500/stall. 40pcs
Fence Barrier | 3000 | $12/fence, 2x2.3m, 200pcs, $500 delivery fee
Printing of Culinary Passports | 13952 | $1.74/booklet, 8-page booklet, 8000pcs
Printing of Fence Banners | 1113.16 | $11.72/banner, 2x2m, 95pcs
Printing of Promotional Banner | 557 | 3x5m, 1pc
Walkie Talkie | 816 | $8/day, Baofeng BF-888s, 34pcs
Total | 76508.16
Marketing
Social Media Paid Ads | 5000 |  | 2 weeks of paid social media ads on Visit Singapore's Channels
Event Photography | 2250 | $750/day, 3 days
Microsite Development | 3000
Total | 10250
Permit
SFA Temporary Fair Permit | 60 |  | To be applied 2 weeks before event
SPF Class 5A Liquor Licence | 44
SCDF (P&FM) storage licence (Gaseous) | 184 |  | Not exceeding 500L
SCDF Temporary Change of Use | 60
BCA Advertising License | 8575
Public Entertainement License | 44
Total | 8967
Insurance
Income Event Liability Plan | 1526 |  | Inclusive of $125 additional coverage and $126 GST surcharge
Total | 1526
Sponsorships |  | Support %
Singapore Airlines |  | 12%
Nestle -Milo |  | 9%
Tiger Beer |  | 6%
GrabFood |  | 3%
Total | 0 | 30%
Transportation
LCH 10 FEET LORRY RENTAL | 120
LCH 24 FEET LORRY RENTAL | 190
Total | 310 |  | Need to consider all the sub-contractors stuff that we are bringing back after teardown
Unrealistic to assume that we can return all sub-contractors items right after the event
Cybersecurity service provider

## Festival Budget
Festival Budget - Hawker Legacy
Budget Summary |  | Summary of Expenses
| Total Expenses |  |  | Expenses
| 192066.324 |  | Rental | 19273.8
| Projected Sponsorship Funding |  | Manpower | 15312.6
| 57619.8972 |  | Logistics | 99383.924
| Projected Revenue from Sales |  | Marketing | 49970
| 47578.13 |  | Permits & Insurance | 3126
|  |  | Other | 5000
|  |  | Uncategorized | 0
|  |  | Total | 192066.324
For Bullet Graph
[6 empty] | Est. Income | Revenue Split STB: 35% Hawkers: 65%
[6 empty] | Expenses | 192066.324
[6 empty] | Y | 0.5
Expenses
| Description |  | Category |  | Quantity | Unit Cost | Amount | Remarks
| 6-Seater Bench Rental |  | Logistics |  | 84 | 150 | 12600 | Rates retrieved from Constellar Exhibition
| Gazebo Tentage Rental |  | Logistics |  | 20 | 600 | 12000 | Rates retrieved from Constellar Exhibition
| Food Stalls Rental |  | Logistics |  | 42 | 500 | 21000 | Industry Estimate
| Lighting Equipment Rental |  | Logistics |  | 1 | 2500 | 2500 | Industry Estimate
| Professional Sound System Rental |  | Logistics |  | 1 | 1500 | 1500 | Rates retrieved from RentProjectorSG
| Walkie-Talkie Rental |  | Logistics |  | 20 | 5 | 100 | Rates retrived from Carousell
| First Aid Kit Rental |  | Logistics |  | 2 | 600 | 1200 | Rates retrieved from Ambulance Medical Services
| Foldable Stretchers Rental |  | Logistics |  | 2 | 210 | 420 | Rates retrieved from Ambulance Medical Services
| 2.3m Fence Barrier Rental |  | Logistics |  | 200 | 12 | 2400 | Rates retrieved from antbuildz
| Portable Toilet Rental |  | Logistics |  | 8 | 80 | 640 | Industry Estimate
| 2kg Fire Extinguisher Rental |  | Logistics |  | 40 | 36 | 1440 | Rates retrieved from antbuildz
| 50kg Fire Extinguisher Rental |  | Logistics |  | 1 | 450 | 450 | Rates retrieved from antbuildz
| NETS Terminal Rental |  | Logistics |  | 6 | 38 | 228 | Rates retrieved from NETS
| NFC Reader Rental |  | Logistics |  | 46 | 13 | 598 | Industry Estimate
| NFC Chip |  | Logistics |  | 8000 | 0.5 | 4000 | Industry Estimate
| 14kg LPG Gas Cylinder |  | Logistics |  | 25 | 39 | 975 | Rates retrieved from SingGas
| 20mm Gas Regulator |  | Logistics |  | 20 | 60 | 1200 | Rates retrieved from SingGas
| Custom Print Wooden Cutlery Set |  | Logistics |  | 10000 | 0.0137 | 137 | Rates retrieved from Alibaba
| Sandwich Board Frame for Hawker Legends Stalls |  | Logistics |  | 20 | 35 | 700 | Industry Estimate
| Safety Helmet |  | Logistics |  | 6 | 13.96 | 83.76 | Rates retrieved from SafetySam
| Safety Boots |  | Logistics |  | 6 | 12.92 | 77.52 | Rates retrived from SafetySam
| Loudhailer |  | Logistics |  | 6 | 16.3 | 97.8 | Rates retrieved from Element14
| Customised Stamps |  | Logistics |  | 40 | 15 | 600 | Rates retrieved from RubberStampOnline
| Printing of Entrance Banners |  | Logistics |  | 1 | 1288.26 | 1288.26 | Rates retrieved from BotakSign
| Printing of Exit Banners |  | Logistics |  | 1 | 751.48 | 751.48 | Rates retrieved from BotakSign
| Printing of Evacuation Route Map |  | Logistics |  | 10 | 13.63 | 136.3 | Rates retrieved from BotakSign
| Printing of Sandwich Board Menu |  | Logistics |  | 20 | 20.51 | 410.2 | Rates retrieved from BotakSign
| Printing of Storefront Banner for Next Gen Hawkers |  | Logistics |  | 20 | 22 | 440 | Rates retrieved from BotakSign
| Printing of Storefront Banner for Hawker Legend |  | Logistics |  | 20 | 7.5 | 150 | Rates retrieved from BotakSign
| Printing of Culinary Passports |  | Logistics |  | 8000 | 1.745 | 13960 | Rates retrieved from BotakSign
| Printing of 2x2m Fence Banners |  | Logistics |  | 95 | 52.8 | 5016 | Rates retrieved from BotakSign
| Printing of 2x1m Passport Counter Banners |  | Logistics |  | 2 | 35.2 | 70.4 | Rates retrieved from BotakSign
| Truss Framework Rental |  | Logistics |  | 1 | 8000 | 8000 | Industry Estimate
| Printing of Festival Crew T-Shirts |  | Logistics |  | 20 | 7.95 | 159 | Rates retrieved from TJG PRINT
| Water Supply |  | Logistics |  | 265 | 1.66 | 439.9 | Rates retrieved from PUB
| Cooling System |  | Logistics |  | 684 | 1.66 | 1135.44 | Rates retrieved from PUB
| Electric Supply |  | Logistics |  | 6620 | 0.3172 | 2099.864 | Rates retrieved from SP Group
| Lorry Rental for Transport of Purchased items To-and-fro Festival Venue |  | Logistics |  | 2 | 190 | 380 | Rates retrieved from LCH Logistics
| Festival Staff |  | Manpower |  | 13 | 180 | 2340 | Rates retrieved from FastJobs
| 6 Cleaners, General Waste Collectors (GWC), 10 Waste Bins Rental (Natoma) |  | Manpower |  | 1 | 2550 | 2550 | 6 cleaners 10 waste bins Rates retrieved from Natoma
| Security Personnel |  | Manpower |  | 12 | 490.5 | 5886 | Rates retrieved from Suits Security Solutions
| Licenced Electrical Worker |  | Manpower |  | 1 | 3000 | 3000 | Rates retrieved from URA
| Implement Incident Management Process Course |  | Manpower |  | 4 | 148.2 | 592.8 | Rates retrieved from NTUC LearningHub
| WSQ Respond to Fire Incident in Workplace Course |  | Manpower |  | 8 | 85.8 | 686.4 | Rates retrieved from NTUC LearningHub
| CERT First Aid Course |  | Manpower |  | 6 | 42.9 | 257.4 | Rates retrieved from NTUC LearningHub
| Social Media Paid Ads (Meta, IG, TT) |  | Marketing |  | 2 | 5000 | 10000 | -
| Festival Credits for Zermatt's Food Challenge |  | Marketing |  | 40 | 10 | 400 | 40 x $10 Festival Credits
| Social Media Contest Prizes |  | Marketing |  | 20 | 20 | 400 | 20 x $20 Festival Credits
| Mediacorp Radio Ads |  | Marketing |  | 1 | 14670 | 14670 | Rates retrieved from Mediacorp
| Direct Article Press Release (The Smart Local) |  | Marketing |  | 1 | 8500 | 8500 | Rates retrieved from TSL
| Zermatt Neo Engagement |  | Marketing |  | 1 | 8000 | 8000 | Rates retrieved from Zermatt
| Microsite Development (MediaPlus) |  | Marketing |  | 1 | 8000 | 8000 | Average rate retrieved from MediaPlus
| SFA Temporary Fair Permit |  | Permits & Insurance |  | 1 | 60 | 60 | Temporary Fair Permit
| SPF Class 5A Liquor Licence |  | Permits & Insurance |  | 1 | 44 | 44 | Liquor Licence
| SCDF (P&FM) Storage Licence (Liquid) |  | Permits & Insurance |  | 1 | 242 | 242 | P&FM Storage Licence
| SCDF Temporary Change of Use |  | Permits & Insurance |  | 1 | 60 | 60 | Temporary Change of Use
| BCA Advertising License |  | Permits & Insurance |  | 1 | 950 | 950 | Rates from fee calculator Licence Application Fee
| Public Entertainment License |  | Permits & Insurance |  | 1 | 44 | 44 | Public Entertainment Licence
| Income Event Liability Plan |  | Permits & Insurance |  | 1 | 1526 | 1526 | Quote received from customised Income Event Liabilility plan
| URA Event Application Form |  | Permits & Insurance |  | 1 | 200 | 200 | Rates retrieved from URA
| S1 (Event Space) |  | Rental |  | 1 | 6943.5 | 6943.5 | Rates retrieved from URA
| S2 (Event Space) |  | Rental |  | 1 | 11125.5 | 11125.5 | Rates retrieved from URA
| Setup Costs |  | Rental |  | 1 | 602.4 | 602.4 | Rates retrieved from URA
| Teardown Costs |  | Rental |  | 1 | 602.4 | 602.4 | Rates retrieved from URA
| Contingency |  | Other |  | 1 | 5000 | 5000
|  | [42] |  |  |  | Total Expenses | 192066.324
Projected Sponsorship Funding
| Description |  | Calculation |  |  | Amount | Remarks
| Singapore Airlines |  | 192066.32 x 12% = 23047.96 |  |  | 23047.9589 | 12% of total expenses
| Nestlé |  | 192066.32 x 9% = 17285.97 |  |  | 17285.9692 | 9% of total expenses
| Tiger Beer |  | 192066.32 x 6% = 11523.98 |  |  | 11523.9794 | 6% of total expenses
| Grabfood |  | 192066.32 x 3% = 5761.99 |  |  | 5761.9897 | 3% of total expenses
[5 empty] | Total | 57619.8972
Projected Revenue from Sales
| Description |  | Calculation |  |  | Amount | Remarks
| 7,500 expected attendees; 65% of attendees (4,875) expected to collect 10 stamps, 35% of attendees (2,625) expected to only spend minimum top up of $10 |  | $22.50* x 4,875 = $109,687.50 2,625 x $10 = $26,250 $109,687.50 + $26,250 = $135,937.50 35% x $135,937.50 = $47,578.13 |  | Revenue Split STB: 35% Hawkers: 65% | 47578.13 | *Minimum spending to receive 10 stamps = 10 x $2.50 = $25 Minus off $2.50 complementary credits $25 - $2.50 = $22.50 per attendee
[5 empty] | Total | 47578.13